## Portfolio Guide
ENERGY SAVINGS MODEL ¦ PORTFOLIO DEMO
An anonymized Excel case study demonstrating linked assumptions, projections, actuals, cost savings, and CO2 impact.
STORY IN BRIEF
This fictional municipal LED retrofit reduces first-year electricity consumption from a 1,080,000 kWh baseline to 367,300 kWh — a 66.0% reduction. The linked model translates project assumptions into monthly projections, invoice actuals, operating-cost performance, energy-price scenarios, and an estimated 377.73 tonnes of avoided CO2 in Year 1. Yellow cells are illustrative inputs; calculated outputs remain live formulas. All names, identifiers, dates, and figures are invented for portfolio use.
SHEET | PURPOSE
General Data | Project assumptions, guarantee terms, system capacity, and key savings outputs
Projection | Monthly and quarterly projected electricity consumption and cost
Year 1 | Illustrative monthly actuals with quarterly and trend comparisons
Operating Costs | Fifteen-year operating-cost and guaranteed-savings performance
CO2 Impact | Electricity savings and avoided CO2 emissions by year
Cost Comparison | Before/after reconstruction cost composition for Year 1
Energy Price | Fifteen-year price escalation and electricity cost scenario
Average Price | Monthly electricity tariff component model
System Consumption | Fifteen-year system consumption trend

## General Data
PORTFOLIO DEMO | ENERGY SAVINGS REPORT | [7 empty] | DEMO-ESCO-01
Contract Name | Municipal LED Street Lighting Modernization – Portfolio Demo
Contract Number | DEMO-ESCO-2026-01
Contract Date | 2026-01-15
Updated by: | Portfolio Analyst
Last updated: | 2026-08-11
Proposal Number | DEMO-BID-026
Report Date | 2026-08-11
Preparation Phase: | 100%
Implementation Phase: | 100%
Guarantee Phase: | 2.407%
Guarantee Start Date: | 2026-04-01
Guarantee Period (years): | 15
Guarantee End Date: | 2041-04-01
Contract Value: NET | 1850000
Fixtures per Tender: | 1200
Installed Fixtures: | 1175 | 1200
Additional Installed Fixtures: | 25
Remaining Fixtures: | 0
Intervention Fixtures: | 12
Control Systems: | 48
Tender – Bid Form
Reference System Consumption [kWh] | 1080000
Reference Installed Capacity [kW] | 190 |  |  |  |  | January | 435.6333 | 10.89%
Reference Energy Cost | 8600000 | 73504.2735 |  |  |  | February | 361.1333 | 9.031%
Reference Maintenance Cost | 2600000 | 22222.2222 |  |  |  | March | 352.5167 | 8.816%
Reference Operating Cost | 11200000 | 95726.4957 |  |  |  | April | 291.8167 | 7.298%
Reference Electricity Price [RSD/kWh] | 8.2 |  |  |  |  | May | 255.8 | 6.397%
Reference Electricity Price [EUR/kWh] | 0.070085 |  |  |  |  | June | 223.1167 | 5.58%
Guaranteed Annual Operating Cost Savings | 68000 |  |  |  |  | July | 241.25 | 6.033%
[6 empty] | August | 281.0333 | 7.028%
Exchange Rate at Publication | 117 |  |  |  |  | September | 319.6167 | 7.993%
[6 empty] | October | 379.4333 | 9.489%
Installed Capacity [kW] | 190 |  |  |  |  | November | 410.5667 | 10.27%
Guaranteed Consumption [kWh] | 380000 |  |  |  |  | December | 446.8167 | 11.17%
Projected Consumption [kWh] | 399873 | [5 empty] | 3998.7333 | 100%
Projected Annual Electricity Cost | 28025.2872
Projected Annual Maintenance Cost | 0
Annual Electricity Savings [kWh] | 700000
Annual Electricity Cost Savings | 45478.9863
Annual Maintenance Cost Savings | 22222.2222
Annual Service Fee | 18000
Annual Service Fee [%] | 26.47%
Operating Hours | 4000 | 4000
Actual Installed System Capacity | [kW] | [kWh] | [kW] | [kWh]
Without Dimming | 0 | 0 | 0 | 0
With Dimming | 120 |  | 120
71% Dimming | 85.2 | 340800 | 84 | 336000
Σ | 85.2 | 340800 | 84 | 336000
Planned Other Consumers | 10 | 40000 | 10 | 40000
Σ | 95.2 | 380800 | 94 | 376000
Unplanned Additional Consumers | 4.7683 | 19073 | 4.7683 | 19073
Σ | 99.9682 | 399873 | 98.7682 | 395073
PUBLIC LIGHTING SYSTEM CHANGES
Document | Date | Installed Capacity [kW] | Operating Hours | Dimming | Consumption [kWh] | New Total System Consumption | Effective Date | Note
Commissioning Certificate | 46113 | 120 | 4000 | 71% | 340800 | 399873 | 46113 | Initial LED commissioning – fictional demo record
Change Order 01 | 46204 | 4.5 | 4000 | 70% | 12600 | 412473 | 46204 | Added pedestrian-zone lighting – fictional demo record
Optimization Note | 46357 | -3 | 4000 | 74% | -8880 | 403593 | 46357 | Night-time dimming optimization – fictional demo record
Formulas:
ENERGY SAVINGS REPORT = EDATE(B16,[ENERGY SAVINGS REPORT, row above]*12)
Note on B40: Author: Из понуде вредност

## Projection
PORTFOLIO DEMO |  | ENERGY SAVINGS REPORT |  |  |  | DEMO-ESCO-01
DATE AND RECORD
Month | Electricity Consumed [kWh] | Cost excl. VAT [RSD] | Cost excl. VAT [EUR] | Electricity +5% [kWh] | Month | Electricity Consumed [kWh] | Quarter | Electricity +5% [kWh]
January | 43563.297 | 357219.0356 | 3053.1542 | 45741.4619 | January |  | Q1 | 120674.6494
February | 36113.3032 | 296129.0865 | 2531.0178 | 37918.9684 | February
March | 35251.6373 | 289063.4257 | 2470.6276 | 37014.2191 | March
April | 29181.6423 | 239289.4672 | 2045.2091 | 30640.7245 | Total | 0 | Q2 | 80926.9325
May | 25579.9787 | 209755.8251 | 1792.7848 | 26858.9776
June | 22311.6481 | 182955.5142 | 1563.7223 | 23427.2305
July | 24124.9799 | 197824.8351 | 1690.8106 | 25331.2289 |  |  | Q3 | 88399.4263
August | 28103.3099 | 230447.1412 | 1969.6337 | 29508.4754
September | 31961.64 | 262085.4482 | 2240.0466 | 33559.722
October | 37943.3017 | 311135.074 | 2659.2741 | 39840.4668 |  |  | Q4 | 129865.6417
November | 41056.6324 | 336664.386 | 2877.4734 | 43109.4641
December | 44681.6294 | 366389.3612 | 3131.533 | 46915.7109
| 399873 | 3278958.6 | 28025.2872 | 419866.65 |  |  |  | 419866.65
Projection – Original Engineering Model
Month | Electricity Consumed [kWh]
January | 43563.297
February | 36113.3032
March | 35251.6373
April | 29181.6423
May | 25579.9787
June | 22311.6481
July | 24124.9799
August | 28103.3099
September | 31961.64
October | 37943.3017
November | 41056.6324
December | 44681.6294
399873

## Year 1
PORTFOLIO DEMO |  | ENERGY SAVINGS REPORT | [5 empty] | DEMO-ESCO-01
|  | Actual |  |  |  |  | Projection
Year | Month | Electricity Consumed [kWh] | Cost excl. VAT [RSD] | Cost excl. VAT [EUR] | Invoice Consumption excl. Added Loads [kWh] | Cost at Reference Energy Price [EUR] | Projected Consumption [kWh]
2026 | September | 34200 | 280440 | 2396.9231 | 32675.5051 | 2290.0781 | 31961.64 |  | 2238.36 | 2396.9231
2026 | October | 35500 | 291100 | 2488.0342 | 33690.1939 | 2361.1931 | 37943.3017 |  | -2443.3017 | 2488.0342
2026 | November | 37100 | 304220 | 2600.1709 | 35141.6954 | 2462.9222 | 41056.6324 |  | -3956.6324 | 2600.1709
2026 | December | 38000 | 311600 | 2663.2479 | 35868.7915 | 2513.8811 | 44681.6294 |  | -6681.6294 | 2663.2479
2027 | January | 38100 | 312420 | 2670.2564 | 36022.1334 | 2524.6282 | 43563.297 |  | -5463.297 | 2670.2564
2027 | February | 29800 | 244360 | 2088.547 | 28077.4805 | 1967.8234 | 36113.3032 |  | -6313.3032 | 2088.547
2027 | March | 28750 | 235750 | 2014.9573 | 27068.58 | 1897.1142 | 35251.6373 |  | -6501.6373 | 2014.9573
2027 | April | 28500 | 233700 | 1997.4359 | 27108.1044 | 1899.8842 | 29181.6423 |  | -681.6423 | 1997.4359
2027 | May | 24100 | 197620 | 1689.0598 | 22879.8953 | 1603.5482 | 25579.9787 |  | -1479.9787 | 1689.0598
2027 | June | 23500 | 192700 | 1647.0085 | 22435.787 | 1572.4227 | 22311.6481 |  | 1188.3519 | 1647.0085
2027 | July | 24450 | 200490 | 1713.5897 | 23299.2953 | 1632.9421 | 24124.9799 |  | 325.0201 | 1713.5897
2027 | August | 25300 | 207460 | 1773.1624 | 23959.5383 | 1679.2155 | 28103.3099 |  | -2803.3099 | 1773.1624
| Σ | 367300 | 3011860 | 25742.3932 | 348227 | 24405.653 | 399873 |  | -32573 | 25742.3932
-8.146%
Month | Invoice Consumption [kWh]
September | 30200
October | 31850
November | 34200
Total | 96250
| Month 1 | Month 2 | Month 3 | Reporting Period Total
Actual | 34200 | 35500 | 37100 | 106800
Projection | 31961.64 | 37943.3017 | 41056.6324 | 110961.5742
Variance | 2238.36 | -2443.3017 | -3956.6324 | -4161.5742
| 7.003% | -6.439% | -9.637% | -3.75%
| Month 1 | Month 2 | Month 3 | Reporting Period Total
Actual | 38000 | 38100 | 29800 | 105900
Projection | 44681.6294 | 43563.297 | 36113.3032 | 124358.2297
Variance | -6681.6294 | -5463.297 | -6313.3032 | -18458.2297
| -14.95% | -12.54% | -17.48% | -14.84%
| Month 1 | Month 2 | Month 3 | Reporting Period Total
Actual | 28750 | 28500 | 24100 | 81350
Projection | 35251.6373 | 29181.6423 | 25579.9787 | 90013.2583
Variance | -6501.6373 | -681.6423 | -1479.9787 | -8663.2583
| -18.44% | -2.336% | -5.786% | -9.624%
| Month 1 | Month 2 | Month 3 | Reporting Period Total
Actual | 23500 | 24450 | 25300 | 73250
Projection | 22311.6481 | 24124.9799 | 28103.3099 | 74539.9379
Variance | 1188.3519 | 325.0201 | -2803.3099 | -1289.9379
| 5.326% | 1.347% | -9.975% | -1.731%
Month | Actual [kWh] | Projection [kWh] | Average [kWh] | Variance [kWh]
September | 34200 | 43563.297 | 30608.3333 | -9363.297
October | 35500 | 36113.3032 | 30608.3333 | -613.3032
November | 37100 | 35251.6373 | 30608.3333 | 1848.3627
December | 38000 | 29181.6423 | 30608.3333 | 8818.3577
January | 38100 | 25579.9787 | 30608.3333 | 12520.0213
February | 29800 | 22311.6481 | 30608.3333 | 7488.3519
March | 28750 | 24124.9799 | 30608.3333 | 4625.0201
April | 28500 | 28103.3099 | 30608.3333 | 396.6901
May | 24100 | 31961.64 | 30608.3333 | -7861.64
June | 23500 | 37943.3017 | 30608.3333 | -14443.3017
July | 24450 | 41056.6324 | 30608.3333 | -16606.6324
August | 25300 | 44681.6294 | 30608.3333 | -19381.6294

## Operating Costs
PORTFOLIO DEMO |  | ENERGY SAVINGS REPORT |  |  |  |  | DEMO-ESCO-01
Guarantee Year | Maintenance Cost | Electricity Cost at Reference Price | Operating Cost | Operating Cost Savings Achieved | Variance vs Guaranteed Savings | Variance [%]
1 | 0 | 24405.653 | 24405.653 | 71320.8427 | 3320.8427 | 4.884% |  | OK | ✔
2 | 0 | 27576.2584 | 27576.2584 | 68150.2373 | 150.2373 | 0.2209% |  | OK | ✔
3 | 0 | 28180.8679 | 28180.8679 | 67545.6279 | -454.3721 | -0.6682% |  | OK | ✔
4 | 0 | 28798.7334 | 28798.7334 | 66927.7623 | -1072.2377 | -1.577% |  | OK | ✔
5 | 0 | 29430.1456 | 29430.1456 | 66296.3501 | -1703.6499 | -2.505% |  | OK | ✔
6 | 0 | 30075.4016 | 30075.4016 | 65651.0942 | -2348.9058 | -3.454% |  | OK | ✔
7 | 0 | 30734.8048 | 30734.8048 | 64991.691 | -3008.309 | -4.424% |  | OK | ✔
8 | 0 | 28345 | 28345 | 67381.4957 | -618.5043 | -0.9096% |  | OK | ✔
9 | 0 | 25234 | 25234 | 70492.4957 | 2492.4957 | 3.665% |  | OK | ✔
10 | 0 | 25000 | 25000 | 70726.4957 | 2726.4957 | 4.01% |  | OK | ✔
11 | 0 | 25555 | 25555 | 70171.4957 | 2171.4957 | 3.193% |  | OK | ✔
12 | 0 | 24987 | 24987 | 70739.4957 | 2739.4957 | 4.029% |  | OK | ✔
13 | 0 | 26987 | 26987 | 68739.4957 | 739.4957 | 1.087% |  | OK | ✔
14 | 0 | 25678 | 25678 | 70048.4957 | 2048.4957 | 3.012% |  | OK | ✔
15 | 0 | 25900 | 25900 | 69826.4957 | 1826.4957 | 2.686% |  | OK | ✔

## CO2 Impact
PORTFOLIO DEMO |  | ENERGY SAVINGS REPORT | [8 empty] | DEMO-ESCO-01
0 | Reference System Consumption [kWh] | 1080000 | 0.00053 | CO2 Emissions Before Reconstruction | 572.4 | Savings [%] | Electricity Savings [kWh] | CO2 Reduction [t] | CO2 Before Reconstruction | CO2 After Reconstruction | CO2 Reduction [t] | Savings [%] | Electricity Savings [kWh]
1 | Consumption in Guarantee Year 1 [kWh] | 367300 | 0.00053 | CO2 Emissions in Year 1 | 194.669 | 65.99% | 712700 | 377.731 | 572.4 | 194.669 | 377.731 | 65.99% | 712700
2 | Consumption in Guarantee Year 2 [kWh] | 366198.1 | 0.00053 | CO2 Emissions in Year 2 | 194.085 | 66.09% | 713801.9 | 378.315 | 572.4 | 194.085 | 378.315 | 66.09% | 713801.9
3 | Consumption in Guarantee Year 3 [kWh] | 365099.5057 | 0.00053 | CO2 Emissions in Year 3 | 193.5027 | 66.19% | 714900.4943 | 378.8973 | 572.4 | 193.5027 | 378.8973 | 66.19% | 714900.4943
4 | Consumption in Guarantee Year 4 [kWh] | 364004.2072 | 0.00053 | CO2 Emissions in Year 4 | 192.9222 | 66.3% | 715995.7928 | 379.4778 | 572.4 | 192.9222 | 379.4778 | 66.3% | 715995.7928
5 | Consumption in Guarantee Year 5 [kWh] | 362912.1946 | 0.00053 | CO2 Emissions in Year 5 | 192.3435 | 66.4% | 717087.8054 | 380.0565 | 572.4 | 192.3435 | 380.0565 | 66.4% | 717087.8054
6 | Consumption in Guarantee Year 6 [kWh] | 361823.458 | 0.00053 | CO2 Emissions in Year 6 | 191.7664 | 66.5% | 718176.542 | 380.6336 | 572.4 | 191.7664 | 380.6336 | 66.5% | 718176.542
7 | Consumption in Guarantee Year 7 [kWh] | 360737.9876 | 0.00053 | CO2 Emissions in Year 7 | 191.1911 | 66.6% | 719262.0124 | 381.2089 | 572.4 | 191.1911 | 381.2089 | 66.6% | 719262.0124
8 | Consumption in Guarantee Year 8 [kWh] | 359655.7736 | 0.00053 | CO2 Emissions in Year 8 | 190.6176 | 66.7% | 720344.2264 | 381.7824 | 572.4 | 190.6176 | 381.7824 | 66.7% | 720344.2264
9 | Consumption in Guarantee Year 9 [kWh] | 358576.8063 | 0.00053 | CO2 Emissions in Year 9 | 190.0457 | 66.8% | 721423.1937 | 382.3543 | 572.4 | 190.0457 | 382.3543 | 66.8% | 721423.1937
10 | Consumption in Guarantee Year 10 [kWh] | 357501.0759 | 0.00053 | CO2 Emissions in Year 10 | 189.4756 | 66.9% | 722498.9241 | 382.9244 | 572.4 | 189.4756 | 382.9244 | 66.9% | 722498.9241
11 | Consumption in Guarantee Year 11 [kWh] | 356428.5727 | 0.00053 | CO2 Emissions in Year 11 | 188.9071 | 67% | 723571.4273 | 383.4929 | 572.4 | 188.9071 | 383.4929 | 67% | 723571.4273
12 | Consumption in Guarantee Year 12 [kWh] | 355359.287 | 0.00053 | CO2 Emissions in Year 12 | 188.3404 | 67.1% | 724640.713 | 384.0596 | 572.4 | 188.3404 | 384.0596 | 67.1% | 724640.713
13 | Consumption in Guarantee Year 13 [kWh] | 354293.2091 | 0.00053 | CO2 Emissions in Year 13 | 187.7754 | 67.2% | 725706.7909 | 384.6246 | 572.4 | 187.7754 | 384.6246 | 67.2% | 725706.7909
14 | Consumption in Guarantee Year 14 [kWh] | 353230.3295 | 0.00053 | CO2 Emissions in Year 14 | 187.2121 | 67.29% | 726769.6705 | 385.1879 | 572.4 | 187.2121 | 385.1879 | 67.29% | 726769.6705
15 | Consumption in Guarantee Year 15 [kWh] | 352170.6385 | 0.00053 | CO2 Emissions in Year 15 | 186.6504 | 67.39% | 727829.3615 | 385.7496 | 572.4 | 186.6504 | 385.7496 | 67.39% | 727829.3615
15-Year Total | [8 empty] | 8586 | 2859.5043 | 5726.4957 | 66.7% | 10804708.8544

## Cost Comparison
PORTFOLIO DEMO |  | ENERGY SAVINGS REPORT |  | DEMO-ESCO-01
| Guarantee Year 1 | Without Reconstruction | After Reconstruction
| Electricity | 79344.9231 | 26984.6206
| Maintenance | 22222.2222
| Service Fee |  | 18000
| TOTAL | 101567.1453 | 44984.6206
| SAVINGS |  | 56582.5247

## Energy Price
PORTFOLIO DEMO |  | ENERGY SAVINGS REPORT | [6 empty] | DEMO-ESCO-01
Reference System Consumption [kWh] | 1080000
Reference Electricity Price | 8.2
Exchange Rate | 117
Guarantee Year | Before Reconstruction | Without Reconstruction | Increase | % | After Reconstruction | Electricity Savings [%] | Electricity Price | Price Increase
1. year | 73504.2735 | 79344.9231 | 5840.6496 | 7.946% | 26984.6206 | 63.29% | 8.5957 | 4.826%
2. year | 73504.2735 | 81328.5462 | 7824.2726 | 10.64% | 27576.2584 | 62.48% | 8.8106 | 7.446%
3. year | 73504.2735 | 83361.7598 | 9857.4863 | 13.41% | 28180.8679 | 61.66% | 9.0309 | 10.13%
4. year | 73504.2735 | 85445.8038 | 11941.5303 | 16.25% | 28798.7334 | 60.82% | 9.2566 | 12.89%
5. year | 73504.2735 | 87581.9489 | 14077.6754 | 19.15% | 29430.1456 | 59.96% | 9.488 | 15.71%
6. year | 73504.2735 | 89771.4976 | 16267.2241 | 22.13% | 30075.4016 | 59.08% | 9.7252 | 18.6%
7. year | 73504.2735 | 92015.7851 | 18511.5116 | 25.18% | 30734.8048 | 58.19% | 9.9684 | 21.57%
8. year | 73504.2735 | 94316.1797 | 20811.9062 | 28.31% | 31408.6653 | 57.27% | 10.2176 | 24.6%
9. year | 73504.2735 | 96674.0842 | 23169.8107 | 31.52% | 32097.3003 | 56.33% | 10.473 | 27.72%
10. year | 73504.2735 | 99090.9363 | 25586.6628 | 34.81% | 32801.0336 | 55.38% | 10.7349 | 30.91%
11. year | 73504.2735 | 101568.2097 | 28063.9362 | 38.18% | 33520.1963 | 54.4% | 11.0032 | 34.19%
12. year | 73504.2735 | 104107.4149 | 30603.1414 | 41.63% | 34255.1266 | 53.4% | 11.2783 | 37.54%
13. year | 73504.2735 | 106710.1003 | 33205.8268 | 45.18% | 35006.1703 | 52.38% | 11.5603 | 40.98%
14. year | 73504.2735 | 109377.8528 | 35873.5793 | 48.8% | 35773.6805 | 51.33% | 11.8493 | 44.5%
15. year | 73504.2735 | 112112.2991 | 38608.0256 | 52.52% | 36558.0185 | 50.26% | 12.1455 | 48.12%

## Average Price
PORTFOLIO DEMO |  | ENERGY SAVINGS REPORT | [5 empty] | DEMO-ESCO-01
Guarantee Year 1
Year | Month | Energy Price | Distribution Charge | System Fee | Efficiency Fee | Excise Factor | Net Price
1 | January | 5.08 | 2.808 | 0.093 | 0.015 | 1.075 | 8.5957
1 | February | 5.08 | 2.808 | 0.093 | 0.015 | 1.075 | 8.5957
1 | March | 5.08 | 2.808 | 0.093 | 0.015 | 1.075 | 8.5957
1 | April | 5.08 | 2.808 | 0.093 | 0.015 | 1.075 | 8.5957
1 | May | 5.08 | 2.808 | 0.093 | 0.015 | 1.075 | 8.5957
1 | June | 5.08 | 2.808 | 0.437 | 0.015 | 1.075 | 8.9655
1 | July | 5.35 | 3.221 | 0.437 | 0.015 | 1.075 | 9.6997
1 | August | 5.35 | 3.221 | 0.437 | 0.015 | 1.075 | 9.6997
1 | September | 5.35 | 3.221 | 0.437 | 0.015 | 1.075 | 9.6997
1 | October | 5.35 | 3.221 | 0.437 | 0.015 | 1.075 | 9.6997
1 | November | 5.35 | 3.221 | 0.437 | 0.015 | 1.075 | 9.6997
1 | December | 5.35 | 3.221 | 0.437 | 0.015 | 1.075 | 9.6997
9.1785

## System Consumption
PORTFOLIO DEMO | ENERGY SAVINGS REPORT |  | DEMO-ESCO-01
Guarantee Year | Total System Electricity Consumption [kWh] | Consumption excl. Additional Loads [kWh]
1 | 367300 | 348227
2 | 366198.1 | 347182.319
3 | 365099.5057 | 346140.772
4 | 364004.2072 | 345102.3497
5 | 362912.1946 | 344067.0427
6 | 361823.458 | 343034.8415
7 | 360737.9876 | 342005.737
8 | 359655.7736 | 340979.7198
9 | 358576.8063 | 339956.7807
10 | 357501.0759 | 338936.9103
11 | 356428.5727 | 337920.0996
12 | 355359.287 | 336906.3393
13 | 354293.2091 | 335895.6203
14 | 353230.3295 | 334887.9334
15 | 352170.6385 | 333883.2696